## Sheet1
| E-foundry - NKN |  | Not received
Received
Month-Year | Task | Days
Apr – 14 | Implementation of mouse picking for STL model | 7
| Added STL editing functions with mouse selection | 13
| Tested functions on various STL low complexity models | 3
| Refining of UI and final testing before implementation | 3
Mar – 14 | Identified new JavaScript library for mouse-picking | 3
| Reviewed and Identified Ray-casting technique | 5
| Converted code from JSC3D to new ThreeJS library | 10
| Refined plane selection algorithm with better data-structures | 7
2014-02-14 | Plane extraction from 3D Model | 7
| Extruding feature added along fixed plane | 7
| Scale, Move, and Rotate functions added | 7
| Testing features on multiple STL files | 4
2014-01-01 | STL file input and rendering with WebGL | 10
| Web User-Interface Development | 7
| Editing & Interaction feature development for website | 7